UNIT 2: AGILE MINI-PROJECT

Student Record and Academic Management Platform

Agile Project Planning Report

Submitted by:

Student Name: Pranjal Daghale Umesh

PRN no:- 2126UMLF2537

Class / Division: AIML-DSY-B

Subject: DEVops and Cloud

College / University: Sanjivani University

Academic Year:2026 - 2027

# Table of Contents

1. Introduction

2. Activity 1 – Study the Business Problem and Product Vision

3. Activity 2 – Agile Product Vision

4. Activity 3 – Scrum Team Structure and Roles

5. Activity 4 – Project Epics

6. Activity 5 – User Stories

7. Activity 6 – Acceptance Criteria

8. Activity 7 – Prioritized Product Backlog

9. Activity 8 – Story Point Estimation

10. Activity 9 – Sprint Planning and Sprint Backlogs

11. Activity 10 – Scrum Board

12. Activity 11 – Simulated Scrum Ceremonies

13. Burndown Chart

14. Sprint Review Report

15. Sprint Retrospective Report

16. Activity 12 – Agile Framework Comparison

17. Project Timeline and Release Roadmap

18. Risks and Mitigation

19. Conclusion

Appendix A – Definition of Done

# 1. Introduction

The Student Record and Academic Management Platform is a proposed web-based application for centralizing student information and common academic activities. It is intended to help authorized administrators, faculty members and students access relevant information efficiently. This report applies Agile planning practices, with Scrum as the recommended framework, to organize the product into Epics, User Stories, a prioritized Product Backlog and short development Sprints.

This is a planning and simulation document. The team should replace sample team assignments, estimates, meeting notes and progress values with actual details where available. Any simulated meeting or illustrative chart must be labelled as such.

# 2. Activity 1 – Study the Business Problem and Product Vision

## 2.1 Business Problem

Educational institutions may maintain student details, course information, attendance and marks in separate spreadsheets, paper registers or disconnected applications. This can lead to duplicated data, inconsistent records, time-consuming searches, delayed reports and avoidable manual errors. A centralized platform can improve organization, access and reporting while applying appropriate security controls.

## 2.2 Stakeholders

| Stakeholder | Interest / Need |
| --- | --- |
| Administrator | Manage student profiles, courses, accounts and reports. |
| Faculty Member | Record attendance and marks; view assigned course information. |
| Student | View personal academic information, attendance and results. |
| Institution Management | Review academic summaries and institutional reports. |
| IT / Support Staff | Maintain system availability, backups and access controls. |

## 2.3 Functional Requirements

- The system shall authenticate registered users.

- The system shall support adding, viewing, searching and updating student records.

- Authorized users shall manage course information and student-course assignments.

- Faculty members shall record and view attendance for assigned courses.

- Authorized faculty members shall enter and update marks.

- The system shall calculate grades according to institution-defined rules.

- Students shall be able to view their permitted academic information.

- The system shall generate student, attendance, course and performance reports.

- The system may provide examination, attendance and result notifications.

## 2.4 Non-Functional Requirements

- Security: authentication, authorization and protection of personal academic data.

- Usability: clear navigation, readable forms and understandable error messages.

- Performance: common searches and record operations should respond within an acceptable time under expected load.

- Reliability: validated records should be saved consistently, with suitable backup and recovery practices.

- Maintainability: modular design and documented code should support future changes.

- Compatibility: the web application should work on commonly used modern browsers and responsive screen sizes.

- Privacy: users should only see data necessary for their role and permissions.

## 2.5 User Personas

| Persona | Goals | Main Features |
| --- | --- | --- |
| Administrator | Maintain accurate institutional records. | Student management, courses, accounts, reports. |
| Faculty Member | Manage teaching and assessment records. | Course list, attendance, marks, performance reports. |
| Student | Check personal academic progress. | Profile, attendance, results, notifications. |

## 2.6 Proposed MVP

The Minimum Viable Product (MVP) will include secure login, basic student record management, course management, attendance recording, marks entry and simple reports. Advanced analytics, automated notification channels and integrations can be considered after feedback from the initial release.

## 2.7 Product Roadmap Review

| Stage | Scope |
| --- | --- |
| Foundation | Requirements, UI prototype, database design and authentication. |
| Core Records | Student and course management. |
| Academic Operations | Attendance and marks management. |
| Visibility | Reports, student result viewing and basic notifications. |
| Improvement | User feedback, security review, usability improvements and optional integrations. |

# 3. Activity 2 – Agile Product Vision

## 3.1 Product Vision Statement

To develop a secure, user-friendly and scalable Student Record and Academic Management Platform that enables educational institutions to manage student records, courses, attendance, academic performance and reports efficiently through a centralized web-based application.

## 3.2 Product Objective

The objective is to reduce repetitive manual work, improve the consistency of academic records, make information easier to retrieve and provide role-appropriate access to academic information.

## 3.3 Expected Business Benefits

- Reduced duplication of student information.

- Faster retrieval of records and generation of reports.

- Improved visibility of attendance and academic performance.

- Clearer responsibility for maintaining records.

- Better protection of information through role-based access.

## 3.4 Measurable Success Criteria

| Measure | Proposed Success Criterion | How to Verify |
| --- | --- | --- |
| Student record operations | Add, search and update test cases pass. | Functional test checklist. |
| Data validation | Invalid mandatory fields and duplicate IDs are rejected. | Validation test cases. |
| Attendance | Attendance is saved and retrieved for the correct course/date. | Test records and reports. |
| Marks and grades | Results match approved sample calculations. | Calculation test cases. |
| Access control | Users cannot access features outside their assigned role. | Role-based access tests. |
| Reporting | Reports show the correct records for selected filters. | Compare report output with test data. |

## 3.5 Constraints and Assumptions

- The project is developed by a student team within a limited academic schedule.

- The initial release will focus on core features rather than every possible institutional integration.

- Institution-specific grading rules and policies must be confirmed before implementation.

- Student data is sensitive and must be handled only with appropriate authorization.

- Sprint length and estimates are planning assumptions and may be revised after team review.

# 4. Activity 3 – Scrum Team Structure and Roles

Replace the placeholders below with the actual team members and responsibilities.

| Role / Accountability | Assigned Member | Responsibilities |
| --- | --- | --- |
| Product Owner | Member 1: ______________ | Clarifies product needs, orders the Product Backlog and communicates stakeholder priorities. |
| Scrum Master | Member 2: ______________ | Supports Scrum events, helps remove impediments and promotes effective collaboration. |
| Developer | Member 3: ______________ | Contributes to design, coding, testing, integration and documentation. |
| Developer | Member 4: ______________ | Contributes to design, coding, testing, integration and documentation. |

Scrum defines the accountabilities of Product Owner, Scrum Master and Developers. The Developers work collectively to create a usable Increment. For this classroom exercise, the team may assign specific module responsibilities while remaining jointly responsible for quality.

# 5. Activity 4 – Project Epics

| Epic ID | Epic Name | Purpose and Scope |
| --- | --- | --- |
| E1 | Authentication and Security | Provide secure login/logout, password reset and role-based permissions. |
| E2 | Student Management | Create, view, search, update and appropriately remove student records. |
| E3 | Course Management | Create and update courses, view course details and assign students. |
| E4 | Attendance Management | Record attendance by course/date and produce attendance summaries. |
| E5 | Marks and Academic Performance | Enter marks, apply approved grading rules and show results. |
| E6 | Notifications | Provide relevant attendance, examination and result notifications. |
| E7 | Reporting | Generate student, course, attendance and performance reports. |

# 6. Activity 5 – User Stories

| Story ID | Epic | User Story |
| --- | --- | --- |
| US01 | E1 | As a registered user, I want to log in securely so that I can access features permitted for my role. |
| US02 | E1 | As a user, I want to log out so that my account is not left open on a shared device. |
| US03 | E1 | As a user, I want to reset my password so that I can regain access if I forget it. |
| US04 | E2 | As an administrator, I want to add a student so that the institution can maintain a digital student record. |
| US05 | E2 | As an administrator, I want to search for a student so that I can find a record quickly. |
| US06 | E2 | As an administrator, I want to update student details so that the record remains accurate. |
| US07 | E2 | As an authorized administrator, I want to deactivate or delete a permitted student record so that outdated records can be handled according to policy. |
| US08 | E2 | As an authorized user, I want to view a student profile so that I can check relevant information. |
| US09 | E3 | As an administrator, I want to add a course so that course information is available in the system. |
| US10 | E3 | As an administrator, I want to update course details so that course information remains current. |
| US11 | E3 | As an administrator, I want to assign students to courses so that enrollment is recorded. |
| US12 | E3 | As an authorized user, I want to view course details so that I can check course information. |
| US13 | E4 | As a faculty member, I want to record attendance for a course and date so that attendance records remain accurate. |
| US14 | E4 | As a faculty member, I want to view attendance records so that I can verify entries. |
| US15 | E4 | As a faculty member, I want to generate attendance summaries so that I can monitor attendance. |
| US16 | E5 | As a faculty member, I want to enter examination marks so that student performance is recorded. |
| US17 | E5 | As an authorized faculty member, I want to update marks when corrections are permitted so that records remain accurate. |
| US18 | E5 | As the system, I want to calculate grades using approved rules so that results are consistent. |
| US19 | E5 | As a student, I want to view my published results so that I can track academic performance. |
| US20 | E6 | As a student, I want to receive examination notifications so that I know about upcoming examinations. |
| US21 | E6 | As a student, I want to receive result notifications so that I know when results are published. |
| US22 | E7 | As an administrator, I want to generate student reports so that I can review student records. |
| US23 | E7 | As an administrator, I want to generate course reports so that I can review enrollment information. |
| US24 | E7 | As an authorized user, I want to generate performance reports so that academic outcomes can be reviewed. |

# 7. Activity 6 – Acceptance Criteria

### US01 – Login

- The login page loads and displays the required fields.

- Registered users with valid credentials can log in.

- Invalid credentials show a clear error without revealing sensitive account details.

- Successful login opens the correct role-appropriate dashboard.

- Protected pages cannot be accessed without authentication.

### US04 – Add Student

- The authorized administrator can open the student registration form.

- Required fields are validated before submission.

- Duplicate student IDs are rejected with a clear message.

- Valid details are saved and can be retrieved from the student list.

- A success or failure message is displayed appropriately.

### US05 – Search Student

- An authorized user can search using a supported identifier or name.

- Matching records are displayed accurately.

- No-match searches show a helpful message.

- Only records permitted by the user's role are displayed.

### US09 – Add Course

- An authorized administrator can enter course code, title and required details.

- Required fields are validated.

- Duplicate course codes are rejected.

- The saved course appears in the course list.

### US11 – Assign Students to Courses

- The administrator can select an existing student and course.

- The system prevents invalid or duplicate assignments.

- A valid assignment is saved and visible in the relevant course/student view.

### US13 – Record Attendance

- Faculty can select a course and lecture date for which they are authorized.

- The system lists students enrolled in that course.

- Faculty can mark attendance using the supported statuses.

- Attendance is saved against the correct course, date and student.

- Duplicate submissions are handled safely and attendance can be retrieved.

### US16 – Enter Marks

- Authorized faculty can select the relevant course/examination.

- Marks must be numeric and within the configured maximum.

- Invalid marks are rejected with a clear message.

- Valid marks are saved and associated with the correct student and examination.

### US18 – Calculate Grades

- The system uses institution-approved grading rules.

- Boundary values are handled correctly.

- The displayed grade matches verified test calculations.

- Changes to marks trigger recalculation where required.

### US19 – View Results

- A student can view only their own published results.

- Unpublished results are not exposed to students.

- The displayed marks and grades match saved approved records.

### US22 – Generate Student Reports

- Authorized users can choose supported report filters.

- The report includes records matching the selected filters.

- Displayed totals match the underlying test data.

- An empty result set is handled with a clear message.

Acceptance criteria for the remaining stories should be completed using the same pattern: define valid input, validation/error behavior, successful outcome, access permissions and data accuracy.

# 8. Activity 7 – Prioritized Product Backlog

| Rank | Story ID | Summary | Epic | Priority | Points |
| --- | --- | --- | --- | --- | --- |
| 1 | US01 | Login | E1 | High | 3 |
| 2 | US04 | Add student | E2 | High | 5 |
| 3 | US05 | Search student | E2 | High | 3 |
| 4 | US06 | Update student | E2 | High | 3 |
| 5 | US08 | View student profile | E2 | High | 2 |
| 6 | US09 | Add course | E3 | High | 3 |
| 7 | US10 | Update course | E3 | Medium | 2 |
| 8 | US11 | Assign students to courses | E3 | High | 5 |
| 9 | US13 | Record attendance | E4 | High | 5 |
| 10 | US14 | View attendance | E4 | High | 3 |
| 11 | US16 | Enter marks | E5 | High | 5 |
| 12 | US18 | Calculate grades | E5 | High | 5 |
| 13 | US19 | View published results | E5 | High | 3 |
| 14 | US15 | Attendance summaries | E4 | Medium | 5 |
| 15 | US22 | Student reports | E7 | Medium | 5 |
| 16 | US12 | View course details | E3 | Medium | 2 |
| 17 | US02 | Logout | E1 | High | 1 |
| 18 | US03 | Password reset | E1 | Medium | 5 |
| 19 | US17 | Update marks | E5 | Medium | 3 |
| 20 | US23 | Course reports | E7 | Low | 3 |
| 21 | US24 | Performance reports | E7 | Medium | 5 |
| 22 | US20 | Examination notifications | E6 | Low | 3 |
| 23 | US21 | Result notifications | E6 | Low | 3 |
| 24 | US07 | Deactivate/delete student | E2 | Medium | 5 |

Priorities and estimates are illustrative. The Product Owner should reorder the backlog after discussing business value, dependencies, risk and stakeholder feedback. Story points represent relative effort, not hours.

# 9. Activity 8 – Story Point Estimation

| Points | Relative Meaning | Example |
| --- | --- | --- |
| 1 | Very small | Logout |
| 2 | Small | View course details |
| 3 | Moderate | Login or search student |
| 5 | Large / complex | Add student, record attendance or enter marks |
| 8 | Very large / uncertain | A complex feature that may need further splitting |
| 13 | Very large / highly uncertain | A broad feature that should usually be broken into smaller stories |

Planning Poker process: each team member privately selects a point value, all values are revealed together, members explain different estimates, and the team discusses and agrees on a final estimate. If a story is too large or unclear, split it before estimating.

# 10. Activity 9 – Sprint Planning and Sprint Backlogs

| Sprint | Sprint Goal | Planned Stories | Approx. Points | Expected Deliverable |
| --- | --- | --- | --- | --- |
| Sprint 1 | Foundation and basic student records | US01, US02, US04, US05 | 12 | Login, logout, add student and search student |
| Sprint 2 | Complete core student and course management | US06, US08, US09, US10, US11, US12, US24 | 23 | Student updates/profile and core course management; reporting story US24 may be deferred if capacity is insufficient |
| Sprint 3 | Attendance and marks | US13, US14, US16, US17, US18 | 21 | Attendance and examination marks workflows |
| Sprint 4 | Results, reports and notifications | US03, US07, US15, US19, US20, US21, US22, US23 | 32 | Result viewing, reports, password reset and notifications |

The points shown are planning estimates, not a commitment or measured team velocity. Sprint 2 and Sprint 4 are relatively heavy in this example; redistribute stories based on team capacity, dependencies and the Sprint Goal. The team should select a realistic amount of work rather than force every listed story into a Sprint.

## 10.1 Example Sprint 1 Task Breakdown

| Story | Tasks |
| --- | --- |
| US01 – Login | Confirm login fields; design screen; implement authentication; handle errors; test access control. |
| US02 – Logout | Add logout action; clear session/token safely; redirect to login; test back-navigation behavior. |
| US04 – Add student | Design form; define data fields; implement validation; save record; test duplicates and required fields. |
| US05 – Search student | Build search interface; implement search by supported fields; display results; test no-match cases. |

## 10.2 Sprint Goal and Definition of Done

Sprint 1 Goal: Deliver a usable starting version with authentication and the ability to add and search student records.

- The code is integrated into the shared project repository.

- Acceptance criteria for the story have been checked.

- Relevant functional and validation tests pass.

- Access permissions and data handling have been reviewed.

- No known critical defect prevents the feature from being used.

- Documentation is updated and the Increment is demonstrated to the team.

# 11. Activity 10 – Scrum Board

Example board for Sprint 1. Update it during the Sprint to reflect actual work status.

| Backlog | To Do | In Progress | Testing | Completed |
| --- | --- | --- | --- | --- |
| Password reset (later Sprint) | US02 – Logout | US04 – Add student | US01 – Login | Project repository setup |
| Course reports (later Sprint) | US05 – Search student | — | — | Initial requirements review |
| Notifications (later Sprint) | — | — | — | — |

Move a card from To Do to In Progress when work begins, then to Testing and Completed when it satisfies the team's Definition of Done. A story should not be marked Completed merely because coding has finished.

# 12. Activity 11 – Simulated Scrum Ceremonies

## 12.1 Sprint Planning Record

| Item | Record |
| --- | --- |
| Sprint | Sprint 1 |
| Sprint Goal | Deliver login and basic student record creation/search. |
| Selected Stories | US01, US02, US04, US05 |
| Estimated Scope | Illustrative total: 12 Story Points |
| Expected Increment | A tested basic workflow for authorized login and student records. |
| Risks / Dependencies | Authentication setup, data model agreement and integration between screens and storage. |

## 12.2 Daily Scrum Template

| Member | Yesterday | Today | Impediment |
| --- | --- | --- | --- |
| Member 1 |  |  |  |
| Member 2 |  |  |  |
| Member 3 |  |  |  |
| Member 4 |  |  |  |

Use actual meeting notes, or label completed sample entries as a simulated exercise.

## 12.3 Sprint Review Record

| Item | Example Record |
| --- | --- |
| Sprint | Sprint 1 |
| Demonstrated | Login flow, logout, student registration and student search, if implemented. |
| Feedback | Check whether field labels are clear, validation messages are helpful and search results are easy to understand. |
| Potential Backlog Changes | Improve form validation, clarify search filters or add missing fields based on feedback. |
| Outcome | Record accepted stories and unfinished work; return incomplete items to the Product Backlog for re-planning. |

## 12.4 Sprint Retrospective Record

| Prompt | Example Response / Action |
| --- | --- |
| What went well? | Responsibilities were clear and the team reviewed progress regularly. |
| What did not go well? | Integration or testing started later than planned. |
| What did we learn? | Agree on data fields and interfaces before parallel development. |
| Improvement action | Create shared interface/data definitions and test cases early in the next Sprint. |
| Owner / Due date | ________________ / ________________ |

These are example records. Replace them with your team's actual observations after the simulated or real event.

# 13. Burndown Chart

A burndown chart shows remaining work over the Sprint. The chart below uses illustrative data for the 12-point Sprint 1 scope listed in Section 10, solely to demonstrate the format. Replace it with your team's actual or clearly labelled simulated daily remaining-work values.

| Sprint Day | Ideal Remaining Points | Illustrative Actual Remaining Points |
| --- | --- | --- |
| 1 | 12.0 | 12 |
| 2 | 10.7 | 12 |
| 3 | 9.3 | 10 |
| 4 | 8.0 | 9 |
| 5 | 6.7 | 8 |
| 6 | 5.3 | 7 |
| 7 | 4.0 | 5 |
| 8 | 2.7 | 4 |
| 9 | 1.3 | 2 |
| 10 | 0.0 | 0 |

# 14. Sprint Review Report

| Field | Details to Complete |
| --- | --- |
| Sprint number / dates | Sprint 1 / __________________ |
| Sprint Goal | Deliver a usable starting version with authentication and the ability to add and search student records. |
| Stories completed | ____________________________________ |
| Stories not completed | ____________________________________ |
| Demonstration evidence | Screenshots, test results or demonstration notes. |
| Stakeholder feedback | ____________________________________ |
| Accepted Increment | ____________________________________ |
| Backlog updates | ____________________________________ |

Review the Increment with relevant stakeholders. The Sprint Review is a working session to inspect the outcome and adapt the Product Backlog, not merely a presentation.

# 15. Sprint Retrospective Report

| Area | Observation | Action for Next Sprint | Owner |
| --- | --- | --- | --- |
| Collaboration |  |  |  |
| Quality / Testing |  |  |  |
| Planning / Estimates |  |  |  |
| Tools / Integration |  |  |  |

The team should choose a small number of practical improvement actions and review them in the next Sprint.

# 16. Activity 12 – Agile Framework Comparison

| Framework | Key Characteristics | Suitability |
| --- | --- | --- |
| Scrum | Work is organized into Sprints with a Product Backlog, Sprint Goal, review and retrospective. | Best fit for this small academic team because modules can be delivered incrementally. |
| Kanban | Visualizes workflow, limits work in progress and supports continuous flow. | Useful for ongoing support and tracking small incoming changes. |
| Extreme Programming (XP) | Emphasizes engineering practices such as pair programming, test-driven development and continuous integration. | Useful to strengthen code quality and reduce integration defects. |
| Lean Development | Focuses on customer value, reducing waste and continuous improvement. | Useful for keeping the MVP focused and avoiding low-value features. |
| LeSS | Applies Scrum principles across multiple teams working on one product. | Potentially suitable if the product grows to several coordinated teams. |
| SAFe | Provides structures for coordinating Agile delivery across many teams and organizational levels. | Likely too heavyweight for the current student mini-project, but relevant to large enterprises. |
| Scrum@Scale | Coordinates multiple Scrum teams through a network of Scrum practices and responsibilities. | Useful if the product later needs several Scrum teams to work together. |

## 16.1 Recommendation

Scrum is recommended for the current project because the scope can be divided into features, prioritized and delivered through short Sprints. Sprint Reviews allow the team to collect feedback, while Retrospectives help improve teamwork. The team can borrow XP practices such as automated testing and continuous integration without adopting a larger scaling framework.

# 17. Project Timeline and Release Roadmap

| Period (Proposed) | Milestone | Release / Output |
| --- | --- | --- |
| Week 1–2 | Discovery and foundation | Confirmed requirements, UI/data design, login and initial student records. |
| Week 3–4 | Core record and course management | Student profile operations and course enrollment. |
| Week 5–6 | Academic operations | Attendance and marks entry. |
| Week 7–8 | Reporting and results | Result viewing and core academic reports. |
| Week 9 | Notifications and improvements | Basic notifications, validation and usability refinements. |
| Week 10 | Final testing and demonstration | Regression testing, documentation, demonstration and final review. |

This is a proposed 10-week classroom roadmap, not a fixed commitment. Adjust dates and scope to the actual semester calendar, team availability and faculty expectations.

# 18. Risks and Mitigation

| Risk | Potential Impact | Mitigation |
| --- | --- | --- |
| Unauthorized access | Exposure of student records | Use role-based permissions, secure sessions and access tests. |
| Incorrect or duplicate data | Unreliable academic records | Validate inputs, enforce unique identifiers and test edge cases. |
| Unclear grading rules | Incorrect grades or results | Confirm grading policy with the institution and test boundary values. |
| Integration delays | Sprint goals may be missed | Agree on data models and interfaces early; integrate frequently. |
| Scope growth | Core features may remain unfinished | Prioritize MVP requirements and defer lower-value features. |
| Data loss | Loss of academic information | Plan backups and test recovery procedures where applicable. |
| Missed requirements | Stakeholder dissatisfaction | Review user stories and acceptance criteria before development. |

# 19. Conclusion

This report demonstrates how Agile planning can be applied to the Student Record and Academic Management Platform. The application is divided into Epics and User Stories, prioritized through a Product Backlog, estimated with Story Points and planned across Sprints. Scrum events, a Scrum Board, a burndown chart and review/retrospective records support transparency and continuous improvement. Scrum is recommended for the current project because it supports incremental delivery, frequent feedback and shared team responsibility.

# Appendix A – Definition of Done

- The story meets its acceptance criteria.

- Code is reviewed or checked according to the team's agreed practice.

- Relevant tests pass and defects are documented.

- Access control and data validation are verified where applicable.

- The feature is integrated into the working application.

- Documentation is updated.

- The team can demonstrate the completed Increment.